## Project Overall Timeline

| Phase | Q1 2020 | Q2 2020 | Q3 2020 | Q4 2020 | Q1 2021 | Q2 2021 |
| --- | --- | --- | --- | --- | --- | --- |
| Analysis |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |
| Development |  |  |  |  |  |  |
| Implementation |  |  |  |  |  |  |
| Evaluation |  |  |  |  |  |  |

## Implementation Detailed Timeline: Training Implementation and Management

| Phase Tasks, Milestones and/or Deliverables |  | Start Date |  | End Date | Responsible Role |  |
| --- | --- | --- | --- | --- | --- | --- |
| Implement Readiness Activities (as necessary) | 08/23/20 |  | 08/28/20 |  |  | Project Manager |
| Prepare for Roll-Out | 09/01/20 |  | 09/30/20 |  |  | Project Manager |
| Secure Training Facilities | 10/01/20 |  | 10/31/20 |  |  | Project Manager |
| Purchase or Print Session Materials | 10/01/20 |  | 10/31/20 |  |  | Project Manager |
| Contract Trainers | 10/01/20 |  | 10/31/20 |  |  | Project Manager |
| Prepare Trainers (“Train-the-Trainer” Sessions) | 11/01/20 |  | 11/15/20 |  |  | Project Manager |
| Create Training Schedule | 11/01/0 |  | 11/15/20 |  |  | Project Manager |
| Create and Distribute Marketing Materials | 11/01/20 |  | 11/15/20 |  |  | Project Manager |
| Register Participants | 11/15/20 |  | 12/31/20 |  |  | Project Manager |
| Create Rosters, Tent Cards, etc. | 12/15/20 |  | 12/31/20 |  |  | Project Manager |
| Hold Training Sessions | 01/02/21 |  | 01/31/21 |  |  | Trainer(s) |
| Evaluate Training (Levels 1-3) at intervals | 02/01/21 |  | 03/31/21 |  |  | Project Manager, Instructional Designer, Trainer(s), Direct Supervisors |

# Estimated Resources for Implementation Phase

[In this section list the resources and time estimate (percentage or effort in hours) to be devoted to Design.

NOTE:  Roles listed and estimates may vary, depending upon the project. The following table is an example only.]

| Resources Required |  |  |  |
| --- | --- | --- | --- |
| Human Resources |  |  |  |
| Role | Duration | Effort | Estimated Total |
| Project manager/ Instructional designer | 9 months | 20 hours per week | 720 |
| Administrative | 9 months | 8 hours per week | 288 |
| Content experts | 3months | 20 hours per week | 240 |
| Graphic designer | 3 months | 40 hours per week | 480 |
| Writer/Editor | 3 months | 16 hours per week | 192 |
| Trainers | 3 months | 16 hours per week | 192 |
| Total Human Resources |  |  | 2112 |
| Tools and Other Resources |  |  |  |
| Resource | Number / Amount | Unit Cost | Estimated Total |
| System Access Permissions | 16 | 0 | 0 |
| Training Database | 1 | * | - |
| Total Resources |  |  |  |

*IT department estimates of costs for additional database already planned in the IT plan.

All resources requested are on staff and available. Technical requirements for the training database will be provided by the IT department.